## Sheet1
Schedule Management
Team-03, Section-02, Dr. Denise Case
Project Name: Lost Treasure | Date: 08/23/2020
Client Name: Dr. Denise Case
Project Manager: Rajeshwari Rudravaram
Start Date: 08/19/2020
End Date: 05/05/2021
Work Breakdown Structure Categories | Start Date | End Date | Estimated Hours per person | [5 empty] | Total
|  |  | Rajeshwari | Vishal | Nooka Raju | Chandrakanth | Rohith | Puneeth
1. Initiating | 2020-08-19 | 2020-08-25 | 2 | 2 | 2 | 2 | 2 | 2 | 12
2. Planning | 2020-08-26 | 2020-09-10 | 2 | 2 | 2 | 2 | 2 | 2 | 12
3. Designing | 2020-09-11 | 2020-12-09
3.1 UI Design | 2020-09-11 | 2020-10-12 | 1 | 1 | 2 | 4 | 2 | 2 | 12
3.2 Synthesis of Design | 2020-10-13 | 2020-10-25 | 3 | 2 | 1 | 2 | 3 | 1 | 12
3.3 Implementation Iteration | 2020-10-26 | 2020-11-28 | 2 | 2 | 3 | 1 | 2 | 2 | 12
3.4 Early release and Contract finalization | 2020-11-29 | 2020-12-09 | 4 | 3 | 1 | 2 | 1 | 1 | 12
4. Implementation | 2021-01-22 | 2021-03-20
4.1 Application Development | 2021-01-22 | 2021-02-25 | 2 | 1 | 2 | 2 | 4 | 1 | 12
4.2 PWA Implementation | 2021-02-26 | 2021-03-20 | 1 | 3 | 3 | 2 | 2 | 1 | 12
5. Monitoring and Controlling | 2021-03-22 | 2021-04-12 | 2 | 1 | 1 | 2 | 1 | 5 | 12
6. Closing | 2021-04-13 | 2021-05-05 | 2 | 2 | 3 | 2 | 2 | 1 | 12
|  | Total | 21 | 19 | 20 | 21 | 21 | 18 | 120