## Sheet1
Project Cost Estimation
Team-03, Section-02, Dr. Denise Case
Work Breakdown Structure Categories | Total Team Cost | No. of Hours per week | Total cost per week | Total cost for three sprints | Team Member | Role | Hourly Rate
Initiating | 340 | 8 | 2720 | 16320 | Rajeshwari Rudravaram | Team Lead | 70
Planning | 340 | 12 | 4080 | 24480 | Puneeth Annam | QA Analyst | 45
Designing | 340 | 12 | 4080 | 24480 | Rohith Chittimalla | Senior Developer | 60
UI Design | 0 | 4 | 0 | 0 | Chandrakanth Polisetty | UI Developer | 52
Synthesis of Design | 0 | 4 | 0 | 0 | Nooka Raju Boddu | Frontend Developer | 55
Implementation Iteration | 0 | 4 | 0 | 0 | Vishal Reddy Vennavaram | Backend Developer | 58
Early release and contract finalization | 0 | 3 | 0 | 0
Implementation | 340 | 12 | 4080 | 24480
Application Development | 0 | 5 | 0 | 0
PWA Implementation | 0 | 4 | 0 | 0
Android/IOS implementation | 0 | 3 | 0 | 0
Monitoring and controlling | 340 | 10 | 3400 | 20400
Closing | 340 | 10 | 3400 | 20400
Total |  |  |  | 130560
Project Name: Lost Treasure
Client Name: Dr.Case
Project Manager:Rajeshwari Rudravaram
Start Date:08/19/2020
End Date:12/09/2020